## Slide 1: Smart Start Workforce Grants Technical Assistance Plan
Ad Hoc Advisory Group Meeting #12
February 2, 2024
Notes: Bethany
Welcome! Thank you for joining today.

## Slide 2: Today’s goals and agenda
GOALS
Preview proposed technical assistance goals and topics for Smart Start Workforce Grants
Discuss technical assistance roles, key activities, and timeline
Gather input on technical assistance plan
AGENDA
Introductions & reminders
Takeaways from the previous advisory group meeting
Share Smart Start technical assistance topics, activities, and timelines
Hear feedback and questions
Notes: Megan
Reminder we are recording.
Today we are going to share a proposed technical assistance plan for Smart Start Workforce Grants. We will preview technical assistance goals and topics and talk about technical assistance roles, key activities, and a timeline. Throughout the presentation you'll have opportunities to share your thoughts on Padlet, and at the end of the session we'll break out into small groups to further discuss and reflect on the Padlet responses.

## Slide 3: Updated transition year advisory timeline
July-October ‘24
Begin Smart Start grants
Smart Start Workforce Grants cost model, accountability, community engagement
Smart Start Workforce Grants rationale and data, communication, and technical assistance
June 2023
October 2023
June 2024
February 2024
Smart Start Workforce Grants parameters and implementation, Quality Support and Layered Funding
Governor’s budget address
Notes: Megan
As you all know, this fiscal year- July 2023 to July 2024- is a transition year where we are designing Smart Start Child Care with your support and input. We have updated this slide as this work has evolved and this is our latest thinking.
Last month, we wrapped up our discussions on Workforce Grant parameters and criteria.
Today, we’ll introduce a proposed technical assistance plan. This plan is just a draft, and today we’d like your feedback on how to make it better.
IDHS is beginning the budget preparation process for State Fiscal Year 2025 with the Governor’s Office, and the input that this committee had provided over the past several months will help to guide and shape budget proposals for Smart Start Child Care for next year.
As I’ve said before, Smart Start Child Care doesn’t work if it doesn’t work for providers, and your input will help to build a Smart Start that works.
As DHS supports with budget preparation internally over the next few months, we’ll spend our time together here discussing and gathering your input and feedback on communications, training, and technical assistance necessary to help child care providers take full advantage of Smart Start in the next fiscal year.
Following the Governor’s Budget Address in February, we’ll be able to more specifically describe and discuss specifics around the Workforce Compensation program.
We will also begin planning for Smart Start Quality Support and Layered Funding.

## Slide 4: Reminder: Role of the advisory group
Build understanding and alignment on strategic intent and goals
Provide input and feedback throughout the design process
Review and pressure-test relevant cost analyses, potential policy options, and administrative options
Surface any potential risks and opportunities
Support overall plan development and champion it among stakeholder groups
Notes: Megan
As a reminder, the role of the ad hoc advisory group is to:
-build understanding and alignment on strategic intent and goals
-provide input and feedback during the design process
-review and pressure-test relevant cost analyses, and potential policy and administrative options
-surface potential risks and opportunities
-support plan development and champion it among stakeholders

## Slide 5: Summary of Ad Hoc Advisory Meeting 11 (12/8/23)
Common Themes
Communications materials should target different provider types like center-based and home-based providers
Communications should be accessible and available in multiple languages
Ad hoc members mentioned the importance of leveraging partnerships with CCR&Rs and DCFS to identify and contact providers who may be eligible but have not applied for grants
Ad hoc members anticipate providers will need support completing the Smart Start Workforce Grants application and recommend identifying a point person who can assist
Questions and Concerns
Could the first phase of the communications plan provide easily accessible information so providers feel welcomed and well-oriented to the program?
Could Smart Start Workforce Grants include “navigators” similar to ECACE?
Notes: Megan
Let's begin by reflecting on the common themes and questions and concerns from our last session, where we shared a communications plan for Smart Start Workforce Grants. We heard that:
Communications materials should target different provider types like center-based and home-based providers
Communications should be accessible and available in multiple languages
Ad hoc members mentioned the importance of leveraging partnerships with CCR&Rs and DCFS to identify and contact providers who may be eligible but have not applied for grants
Ad hoc members anticipate providers will need support completing the Smart Start Workforce Grants application and recommend identifying a point person who can assist
There also heard questions and concerns including:
Could the first phase of the communications plan provide easily accessible information so providers feel welcomed and well-oriented to the program?
Could Smart Start Workforce Grants include “navigators” similar to ECACE?
We are documenting your questions and using them to inform design and planning, even if we can’t address them right away.

## Slide 6: Technical assistance goals and topics
Notes: Trish

## Slide 7: Smart Start Workforce Grants technical assistance goals
Technical assistance on Smart Start Workforce Grants will support providers to:
  Understand their eligibility and acceptable use of funds for Smart Start Workforce Grant​s
  Explain differences between Transition Grants and Smart Start Workforce Grants
  Complete applications​
  Anticipate the grant’s impact on their budget​
  Prepare for accountability and reporting requirements
  Receive support with business practices that enable successful participation in the program
Notes: Trish
Just as a reminder, Governor Pritzker announced Smart Start Child Care in February of last year, which is an investment in the child care sector. As we have talked about, one part of this initiative is Smart Start Workforce Grants, which will offer child care providers grants to compensate their staff. Those who participate in the program will need to demonstrate that they have paid their staff a required minimum wage. We anticipate that providers will need support to successfully sign up for the program and meet requirements for participation. Part of this program will include training and technical assistance and we anticipate technical assistance will help providers to:
  Understand their eligibility and acceptable use of funds for Smart Start Workforce Grant​s
  Explain differences between Transition Grants and Smart Start Workforce Grants
  Complete applications​
  Anticipate the grant’s impact on their budget​
  Prepare for accountability and reporting requirements
  Receive support with business practices that enable successful participation in the program

## Slide 8: Technical assistance will include topics that focus on technical support and foundational practices
  Technical support to:
  Complete applications and required documentation
  Understand grant requirements
  Submit reporting materials
  Foundational practices that will support participation and success with Smart Start Workforce Grants, such as:
  Business practices including budgeting for staffing and wages
  Enrollment strategy and CCAP navigation
  Finding and utilizing a payroll system
Smart Start technical assistance topics
Notes: Trish
We also expect that providers will need different types of support to participate in the program. They will likely need help with the technical aspect of the program such as completing applications and required documentation, understanding grant requirements, and submitting reporting materials.
Programs will also need support with building foundational practices that enable them to pay staff the required minimums and meet the requirements of the grant. These practices will likely include:
  Strengthening their business practices especially related to budgeting for staffing and wages
  Focusing on enrollment strategy and CCAP navigation
  Finding and utilizing a payroll system

## Slide 9: Technical assistance activities and timeline
Notes: Michelle

## Slide 10: Technical assistance will be based on providers’ and local needs and could include:
Smart Start technical assistance activities
Webinars
Training
Resource documents
Group sessions
One-on-one support
Discussion Question 1: What other technical assistance activities have been helpful for providers to learn about new initiatives and funding opportunities?
Share your responses here: February ad hoc padlet
Notes: Michelle
In addition to the goals and potential topics for technical assistance, we want to describe the types of technical assistance activities that could support providers with Smart Start Workforce Grants.
Technical assistance may look like:
One-on-one support
Group sessions
Resource documents
Webinars
And training
CCR&Rs will work in partnership with INCCRRA to support providers, and CCR&Rs will have flexibility to decide what is most helpful for their communities.
Now that we have shared about the basics of the technical assistance plan, we want to ask you to reflect on the following question: What other technical assistance activities have been helpful for providers to learn about new initiatives and funding opportunities?
We'll ask you use the Padlet link shared in the chat to respond to the question now, and at the end of the meeting we'll revisit these same questions in small discussion groups.

## Slide 11: INCCRRA and CCR&Rs will support providers with technical assistance
Smart Start Workforce Grants technical assistance system
Smart Start Workforce Grants Coordinator at INCCRRA
Smart Start Workforce Grants Local Experts at CCR&Rs
CCR&R staff
Child care programs
Notes: Michelle
Now we want to share about the structure of Smart Start Workforce Grants technical assistance and tell you more about who will provide technical assistance for Workforce Grants.
We heard from the field through focus groups and surveys that providers valued their existing relationships with technical assistance providers.
Based on this feedback, technical assistance for Smart Start Workforce Grants will be delivered through existing relationships at local CCR&Rs.
As you can see from this visual, INCCRRA will hire a Smart Start Workforce Grants Coordinator who will support “Smart Start local experts” at CCR&Rs with resources, tools, data, and information from INCCRRA.
Then the local experts will share knowledge about Smart Start Workforce Grants with staff at their CCR&R who have existing relationships with child care programs. CCR&R staff will then provide technical assistance to child care providers and programs.
IDHS will be in frequent contact with INCCRRA to provide guidance and support throughout implementation of the technical assistance plan.

## Slide 12: Child care programs will share feedback to improve Smart Start Workforce Grants
Smart Start Workforce Grants technical assistance feedback loop
Smart Start Workforce Grants Coordinator at INCCRRA
Smart Start Workforce Grants Local Experts at CCR&Rs
CCR&R staff
Child care programs
Notes: Michelle
This structure will also enable a feedback loop to improve Smart Start Workforce Grants.
For instance, staff at CCR&Rs who work with providers may identify a huge barrier to entry or notice that the majority of programs they work with do not understand a wage floor. CCR&R staff will share this information with their local expert, who will share it with the grants coordinator at INCCRRA
The grants coordinator will then design resources and tools to support programs through technical assistance and share barriers with IDHS.
The feedback loop will inform types of technical assistance support and recommendations to update policies and procedures to ensure equitable access to Smart Start Workforce Grants.

## Slide 13: INCCRRA will manage administrative processes and develop resources for providers.
Smart Start technical assistance system: INCCRRA role
Manage administrative processes
Grant specialists administer the application and reporting processes and provide customer service
INCCRRA help desk troubleshoots technical issues and answers basic grant questions
Develop resources
Hire a dedicated Smart Start Workforce Grants Coordinator who creates training and technical assistance materials for Smart Start Workforce Grants
Organize resource sharing across CCR&Rs
Communicate timely policy changes with CCR&Rs
Answer questions from CCR&Rs about Smart Start Workforce Grants
Notes: Michelle
Let’s go into a little more detail about INCCRRA’s role in Smart Start Workforce Grants technical assistance. INCCRRA will manage administrative processes and develop resources for providers.
This means that INCCRRA’s role will be similar to past grants in terms of managing administrative processes. INCCRA will continue administer the application and reporting process and offer support on technical issues related to applications and reporting through a help desk. INCCRRA will also be available to answer basic questions about Smart Start Workforce Grants through the help desk.
As far as developing resources, INCCRRA will hire a grant coordinator who will create technical assistance materials and organize resource sharing across CCR&Rs. The grants coordinator will train CCR&R local experts on those resources. The coordinator will also stay up to date on policy changes, share updates with CCR&Rs, and be a point of contact for CCR&Rs to ask questions about the grants.

## Slide 14: CCR&Rs will coordinate across the ECE system and provide technical assistance through trusting relationships with providers
Smart Start technical assistance system: CCR&R role
Identify and share barriers to accessing Smart Start Workforce Grants with INCCRRA to inform resource development
Determine a staff member to be a “local expert” to be a point of contact with INCCRRA, receive training on grantee support, and train other CCR&R staff on Smart Start Workforce Grants
Coordinate across the ECE system
Provide technical assistance
Share information about Smart Start Workforce Grants, support providers with applications and reporting, and provide technical assistance on topics relevant to Smart Start Workforce Grants
Build and maintain relationships with programs involved in Smart Start Workforce Grants
Discussion Question 2: Will this proposed technical assistance from INCCRRA and CCR&Rs help providers successfully participate in SSWGs? Why or why not? What is missing here?
Notes: Michelle
The CCR&Rs will coordinate across the ECE system and provide technical assistance to providers through their trusted relationships within their community.
To coordinate across the ECE system, CCR&Rs will choose one “Local Expert” to be the point of contact for Smart Start Workforce Grants for INCCRRA, receive training about workforce grants, and train other CCR&R staff on the grants. They will attend 1-2 workdays at INCCRRA sometime between March and June to receive intensive training on workforce grants, resources available, and areas we anticipate will need technical assistance.
CCR&Rs will also help coordinate across the ECE system by identifying and sharing barriers to accessing Smart Start Workforce Grants with INCCRRA to inform resource development.
CCR&Rs will also provide technical assistance to providers in their community.
After local experts share about workforce grants with other staff at CCR&Rs, multiple staff members at CCR&Rs can provide technical assistance to providers. Technical assistance will likely focus on helping providers with applications and reporting and working with them on foundational practices that will be allow them to successfully participate in the program- like budgeting for staffing and wages.
Let’s pause to hear your feedback. Please use the Padlet to respond to our second discussion question: Will this proposed technical assistance from INCCRRA and CCR&Rs help providers successfully participate in SSWGs? Why or why not? What is missing here?

## Slide 15: Smart Start Workforce Grants technical assistance timeline
February to July 2024 IDHS, INCCRRA, and CCR&Rs will focus on preparing providers to apply for Smart Start Workforce Grants
February
INCCRRA fills SSWG Coordinator position and
CCR&Rs identify local experts
March
April
Spring workdays to train CCR&Rs on SSWG
May
SSWG application details released
June
CCR&Rs will support providers with completing Smart Start applications
July
July 1st
Smart Start Workforce Grant application released
(pending appropriation)
Notes: Michelle
Here is a basic timeline for Smart Start Workforce Grants technical assistance from February to July 2024.
You can see in February INCCRRA will hire the Grant Outreach Coordinator and CCR&Rs will identify their Local Experts.
We anticipate training CCR&Rs about Smart Start Workforce Grants in April and sharing details about the workforce grants application in May.
CCR&Rs will spend June and July helping providers get ready to apply and will support them through the application process beginning in July.

## Slide 16: Equity check for Smart Start Workforce Grants decisions
Equity considerations will also guide Smart Start Workforce Grants training and technical assistance
Center children and families, especially the ELC priority populations, focusing on racial equity
Focus on the needs and priorities of historically disenfranchised children and families, providers, workforce, and communities
Consider how our decisions may benefit or harm historically disenfranchised children and families, providers, workforce, and communities
Seek the expertise and input from stakeholders already engaged with our historically disenfranchised children and families, providers, workforce, and communities
Where possible, consider data that provides insight into the relative impact on historically disenfranchised children and families, providers, workforce, and communities
Notes: Trish
We also want to take this opportunity to revisit our equity check and discuss how equity is being centered in our technical assistance plan. I'll read through these to remind us of the equity considerations:
Center children and families, especially those identified in the recommended and approved ELC priority populations, focusing on racial equity
Focus on the needs and priorities of historically disenfranchised children and families, providers, workforce, and communities
Consider how our decisions may benefit or harm historically disenfranchised children and families, providers, workforce, and communities
Seek the expertise and input from stakeholders already engaged with our historically disenfranchised children and families, providers, workforce, and communities
Where, consider data that provides insight into the relative impact on historically disenfranchised children and families, providers, workforce, and communities
With these in mind, we'll take a look at some approaches we've developed to ensure equity in our technical assistance strategy and hear your feedback and input.

## Slide 17: Equity check for Smart Start Workforce Grants technical assistance
Technical assistance will honor equity commitments by:
Empowering CCR&Rs to design supports that meet the local needs of their community
Creating feedback loops to understand barriers and address challenges so grants are accessible for providers
Offering support in languages other than English, including Spanish
Developing technical assistance and resources unique to homes and center-based programs
Collecting data for further decision-making in subsequent years
D
Discussion Question 3: Will this technical assistance plan support people who are least likely to access the grants? What changes/additions should we make to honor equity commitments?
Notes: Trish
The technical assistance plan will honor the equity considerations we just reviewed in the following ways:
Empowering CCR&Rs to design supports that meet the local needs of their community
Creating feedback loops to understand barriers and address challenges so grants are accessible for providers
Offering support in languages other than English, including Spanish
Developing technical assistance and resources unique to homes and center-based programs
Collecting data for further decision-making in subsequent years
Now, we're going to return to the Padlet to hear from you: Will this technical assistance plan support people who are least likely to access the grants? What changes/additions should we make to honor equity commitments?

## Slide 18: Small Group Discussion
We will split into four groups to discuss the questions posed during the presentation and hear your thoughts on priorities for technical assistance.
Notes: Megan
Thank you all for responding to the discussion questions in Padlet throughout the session. As we mentioned earlier, we'll now have a chance to discuss these same questions in small breakout groups where you can expand on your Padlet answers or raise additional questions or thoughts. We are going to split into four groups to discuss the questions posed during the presentation and hear your thoughts on priorities for technical assistance.

## Slide 19: Discussion Questions
What other technical assistance activities have been helpful for providers to learn about new initiatives and funding opportunities?
Will this proposed technical assistance from INCCRRA and CCR&Rs help providers successfully participate in SSWGs? Why or why not? What is missing here?
Will this technical assistance plan support people who are least likely to access the grants? What changes/additions should we make to honor equity commitments?
Notes: Megan
As a reminder here are the questions again:
What other technical assistance activities have been helpful for providers to learn about new initiatives and funding opportunities?
Will this proposed technical assistance from INCCRRA and CCR&Rs help providers successfully participate in SSWGs? Why or why not? What is missing here?
Will this technical assistance plan support people who are least likely to access the grants? What changes/additions should we make to honor equity commitments?
We will now go into breakout groups and you'll automatically be taken to your group. You'll have about 20 minutes to discuss.
--------
Facilitators:
Lori
Sinthu
Megan
Beza
For facilitators, additional question:
Framing/additional question: What do you think providers will need the most support with for Smart Start Workforce Grants?
Sharing Padlet link at the beginning and then further discuss with small groups.

## Slide 20: Next Meeting Date: March 1, 2024, 11-1pm Meeting topic: Smart Start Workforce Grants parameters including eligibility and award amounts Open Survey for Feedback: https://forms.gle/3DPPyPUcPQiTgbwX9
Notes: Bethany
We are looking forward to seeing you for our next meeting and plan to discuss parameters- including eligibility and award amounts- for Smart Start Workforce Grants.